## RAID Log
RAID LOG
A RAID log is used to manage Risks, Actions, Assumptions, Issues, Decisions and Dependancies on a project.
Guidelines
All tabs have the following fields to be completed:
Number | Record the number of the item in the log using sequential numbering.
Date Raised | Enter the date the item was raised to the project team.
Raised By | Enter the name or initials of the person who raised the item to the project team.
Description | Enter a brief description.
Owner | Enter the owner.
Status | Enter the current status of the item. See the status guidelines table, below.
In addition, each tab has some additional information
Risks | Impact | See Risk Impact & Probability table, below.
Risks | Probability | See Risk Impact & Probability table, below.
Risks | Risk Score | See Risk Impact & Probability table, below.
Risks | Mitigation Type | Enter the type of mitigation action to be used. See mitigation guidelines table, below.
Risks | Detail of mitigating action to be taken | Enter further information about the mitigating action(s) required.
Risks | Actioner | Enter the name or initials of the person who will monitor the risk/undertake the mitigating action.
Assumptions | Reason for Assumption | Enter the reason the assumption has been made.
Assumptions | Action to Validate | Indicate the action required to validate whether the assumption is correct.
Assumptions | Impact if Assumption Incorrect | Indicate the impact on the project if the assumption is found to be incorrect.
Issues | Resolution/Follow On Actions | Indicate the resolution action and/or the follow on actions required.
Issues | Actual Date Closed | Enter the actual issue resolution date.
Issues | Notes | Insert additional notes and/or updates on progress.
Dependencies | Location | Indicate what will deliver the dependent item(s). e.g. another project, BAU Processes.
Dependencies | Deliverables | List the deliverables expected.
Dependencies | Delivery Date | Indicate the expected delivery date for the dependency.
Risk Impact & Probability
Insert value (1-5) for the likelihood (L) and the impact (I) of the risk (if left un-managed), as indicated on the table below. Multiply the values (L*I) to determine the risk score (Sc). Colour-code the ‘Sc’ box accordingly.
IMPACT | Catastrophic = 5 | 5 | 10 | 15 | 20 | 25
| Major = 4 | 4 | 8 | 12 | 16 | 20
| Moderate = 3 | 3 | 6 | 9 | 12 | 15
| Minor = 2 | 2 | 4 | 6 | 8 | 10
| Insignificant =1 | 1 | 2 | 3 | 4 | 5
|  | Rare = 1 | Unlikely =2 | Possible = 3 | Likely =4 | Almost certain = 5
Liklihood
Risk score (Impact * Probability)
High | 15-25 | Unacceptable level of risk, requires constant active monitoring and measures to be put in place to reduce risk.
Medium | 7-14 | Acceptable level of risk exposure subject to regular active monitoring measures.
Low | 1-6 | Acceptable level of risk exposure subject to regular passive monitoring measures.
Status, Priority and Mitigation Guidelines
Priority | Assign priority:
| Critical | Issue will stop project progress if not resolved.
| High | Issue will likely move the project back in terms of budget or timeline, or will materially affect quality or scope.
| Medium | Issue will have material effect on project, has potential to be moved to high category and/or requires significant resources to manage
| Low | Issue is expected to have a moderate effect on the project, but will require resources to address.
Status | What is the status of the issue?
| Open | The issue is currently open but has not yet been addressed.
| Work In Progress | The issue is being actively worked on to develop a resolution.
| Closed | The issue is no longer considered an active project threat and can be closed with or without resolution.
| Closed - Possible next phase | The issue is no longer an active threat but should be suggested for a future project in the Project Closure Report.
Risk Mitigation | What mitigating action should be taken?
| Avoidance | Avoid the risk. |  | e.g. descope risky activities from the project.
| Reduction | Reduce the risk Probability/Impact. |  | e.g. deliver in phases so impact of failure is reduced.
| Transfer | Outsource or insure the risk. |  | e.g. purchase insurance to cover failure.
| Acceptance | Accept and budget for the risk. |  | e.g. add to project budget to deal with risk if it occurrs.

## Risks
Risks
Number | Date Raised | Raised By | Description | Owner | Status | Impact (I) 1-5 (click note for guidance) | Liklihood (L) 1-5 (click note for guidance) | Risk score (I*L) | Mitigation Type | Detail of mitigating action to be taken | Actioner
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on A2: Record number using sequential numbering.
Note on B2: Record the date the risk was first raised with the project team.
Note on C2: Indicate who raised the risk.
Note on D2: Insert a brief description.
Note on E2: Indicate the name/intials of the owner.
Note on F2: Status: Open Work in Progress Closed
Note on G2: 1 = Insignificant 2 = Minor 3 = Moderate 4 = Major, 5 = Catastophic
Note on H2: 1 = rare 2= Unlikely 3 = Possible 4 = Likely 5 = Almost Certain
Note on I2: Automatically calculated Impact * Liklihood 1-6 = Low (green) passive management 7 - 14 = Medium (amber) regular active management 15- 25 = High (red) constant, active management
Note on J2: Mitigation Type: Avoidance = Reduce the Probability of the risk. Reduction = Reduce the Impact of the risk. Transfer = Outsource or insure the risk. Accept = Accept and budget for the risk.
Note on L2: Indicate the name/intials of the actioner(s).

## Assumptions
Assumptions
Number | Date Raised | Raised By | Description | Owner | Status | Reason for Assumption | Action to Validate | Impact if Assumption Incorrect
Note on A2: Record number using sequential numbering.
Note on B2: Record the date the assumption was first raised to the project team.
Note on C2: Indicate who raised the assumption.
Note on D2: Insert a brief description.
Note on E2: Indicate the name/intials of the owner.
Note on F2: Status: Open Work in Progress Closed
Note on G2: Insert the reason for the assumption.
Note on H2: Insert the action required to validate whether or not the assumption is correct.
Note on I2: Describe the impact on the project if the assumption is incorrect.

## Issues
Issue Log
Number | Date Raised | Raised By | Description | Owner | Status | Priority | Resolution/Follow On Actions | Actual Date Closed | Notes
Note on A2: Record number using sequential numbering.
Note on B2: Record the date the issue was first raised with the project team.
Note on C2: Indicate who raised the issue.
Note on D2: Insert a brief description.
Note on E2: Indicate the name/intials of the owner.
Note on F2: Status: Open Work in Progress Closed Closed - Possible Next Phase
Note on G2: Priority: Critical High Medium Low
Note on H2: Indicate the resolution action and/or the follow on actions required.
Note on I2: Indicate the Actual Close Date.
Note on J2: Insert additional notes and/or updates on progress.

## Dependencies
Dependencies
Number | Date Raised | Raised By | Description | Owner | Status | Priority | Location | Deliverables | Delivery Date
Note on A2: Record number using sequential numbering.
Note on B2: Record the date the dependency was first raised with the project team.
Note on C2: Indicate who raised the dependency.
Note on D2: Insert a brief description.
Note on E2: Indicate the name/intials of the owner.
Note on F2: Status: Open Work in Progress Closed
Note on G2: Priority: Critical High Medium Low
Note on H2: Indicate what will deliver the dependent item(s): Another Project BAU Processes
Note on I2: List the deliverables expected.
Note on J2: Indicate the expected delivery date for the dependency.

## Validation Sheet
Risk impact | Risk Probablity
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5